Restaurant Operations & Ordering Platform

Product Backlog

Prioritized user stories for all 14 modules, with acceptance criteria and story-point estimates

Product Owner: Member #1

Scrum Master: Member #2

14 Sprints (1 module / sprint)

# 1. Backlog Overview

The Product Backlog below is the single, prioritized, ordered list of all work for the Restaurant Operations & Ordering Platform. It is owned and ordered by the Product Owner (#1) and refined weekly by the whole Scrum Team during Backlog Refinement. Priority follows two drivers: (1) technical dependency — authentication, customers, menu, and the core order lifecycle must exist before the modules that build on them — and (2) business value — the modules that make up the primary customer-order-to-payment journey are ranked Must, supporting operational modules are ranked Should, and enhancement/insight modules are ranked Could. Modules 11–14 were added to the backlog after the first ten modules were delivered: Sprint 11 (quality, security and operations) and Sprint 12 (staff accounts and the management hierarchy) are ranked Must because they close access-control and account-management gaps in the delivered system; Sprint 13 (attendance) and Sprint 14 (payroll and the workforce hub) build on them and are ranked Should.

| Pri. | Module (Epic) | Sprint | MoSCoW | # Stories | Total Pts |
| --- | --- | --- | --- | --- | --- |
| 1 | Customer Management | Sprint 1 | Must | 5 | 24 |
| 2 | Menu Management | Sprint 2 | Must | 5 | 19 |
| 3 | Order Management | Sprint 3 | Must | 5 | 24 |
| 4 | Kitchen Workflow | Sprint 4 | Must | 5 | 24 |
| 5 | Billing | Sprint 5 | Must | 5 | 24 |
| 6 | Table Management | Sprint 6 | Should | 4 | 16 |
| 7 | Reservations | Sprint 7 | Should | 4 | 16 |
| 8 | Inventory | Sprint 8 | Should | 5 | 27 |
| 9 | Staff Management | Sprint 9 | Could | 5 | 21 |
| 10 | Analytics | Sprint 10 | Could | 6 | 22 |
| 11 | Quality, Security & Operations | Sprint 11 | Must | 7 | 30 |
| 12 | Staff Accounts & Hierarchy | Sprint 12 | Must | 6 | 23 |
| 13 | Attendance & My Work | Sprint 13 | Should | 5 | 22 |
| 14 | Payroll & Workforce Hub | Sprint 14 | Should | 5 | 22 |
|  | TOTAL |  |  | 72 | 314 |

# 2. Detailed Backlog Items by Module

Each module below is an Epic. It is broken into INVEST-style user stories, each with Given/When/Then-style acceptance criteria and a Fibonacci-scale story-point estimate (1, 2, 3, 5, 8, 13…) agreed during Sprint Planning poker.

## Module 1: Customer Management + Core Setup

Sprint: 1  |  Priority: Must  |  Module Lead: #4  |  Stakeholders: Customer, Waiter, Manager, Admin

Sprint Goal: Stand up auth/RBAC for all five roles and deliver customer registration & profile management.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US1.1 | As a Admin, I want authentication and role-based access control (RBAC) set up for all five stakeholder roles, so that each role only sees the features and data it is permitted to access. | - Given a new user registers, when they sign up, then they are assigned exactly one role (Customer, Waiter, Chef, Manager, or Admin). - Given a logged-in user, when they navigate to a route outside their role's permissions, then the system returns a 403 and redirects to their own dashboard. - Given an Admin, when they view the user list, then they can change any user's role. | 8 | Must |
| US1.2 | As a Customer, I want to register and edit my profile, so that my details are saved for future visits and orders. | - Given a new customer, when they submit the registration form with name, contact, and password, then an account is created and they are logged in. - Given a logged-in customer, when they edit their profile, then changes are persisted and reflected immediately. - Given invalid input (e.g., missing required field), when the form is submitted, then a validation error is shown and no record is created. | 5 | Must |
| US1.3 | As a Waiter or Manager, I want to search and filter the customer ledger, so that I can quickly find a customer during service. | - Given the customer ledger, when I search by name, phone, or email, then matching customers are returned within the same view. - Given a filtered result set, when no customer matches, then a clear 'no results' state is shown. | 3 | Must |
| US1.4 | As a Waiter, Manager, or Customer, I want to view a customer's order history and totals, so that we can reference past orders and spend. | - Given a customer profile, when I open the history tab, then all past orders with dates and totals are listed, newest first. - Given a customer with no past orders, when I open the history tab, then an empty state is shown rather than an error. | 5 | Must |
| US1.5 | As a Customer, I want to store my dietary and allergy preferences, so that the kitchen and waiter are aware of restrictions when I order. | - Given a customer profile, when I add allergy/dietary tags, then they are saved and visible to Waiter and Chef on any of my active orders. - Given no preferences set, when a profile is viewed, then the section shows 'none recorded' rather than being blank/broken. | 3 | Must |

## Module 2: Menu Management

Sprint: 2  |  Priority: Must  |  Module Lead: #3  |  Stakeholders: Customer, Waiter, Chef, Manager, Admin

Sprint Goal: Deliver a backend-driven menu with categories, modifiers, and availability control.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US2.1 | As a Manager or Admin, I want to add, edit, and remove menu items, so that the menu always reflects what the kitchen can currently serve. | - Given the menu admin screen, when I create an item with name, price, and description, then it appears on the live customer-facing menu. - Given an existing item, when I edit or delete it, then the change is reflected immediately across all role views. | 5 | Must |
| US2.2 | As a Manager, I want to organize items by category, so that customers and waiters can browse the menu logically. | - Given a set of menu items, when I assign each to a category, then the customer-facing menu groups items under that category heading. - Given a category with no items, when viewed, then it is hidden rather than shown empty. | 3 | Must |
| US2.3 | As a Manager, I want to support modifiers such as size and extras, so that customers can customize dishes at the point of order. | - Given a menu item, when I attach modifier groups (e.g., size, add-ons), then those options appear when the item is added to an order. - Given a modifier with a price delta, when selected, then the order line total updates accordingly. | 5 | Must |
| US2.4 | As a Customer, I want to see dietary and allergen tags on menu items, so that I can make safe and informed choices. | - Given a menu item with tags (e.g., vegan, contains nuts), when displayed, then the tags are visible as badges/icons. - Given a customer with a stored allergy preference, when browsing the menu, then conflicting items are visually flagged. | 3 | Must |
| US2.5 | As a Manager or Chef, I want to control item availability / mark items out-of-stock, so that customers cannot order dishes the kitchen cannot currently prepare. | - Given an item marked unavailable, when a customer views the menu, then the item is shown as out-of-stock and cannot be added to an order. - Given an item re-marked available, when refreshed, then it becomes orderable again immediately. | 3 | Must |

## Module 3: Order Management

Sprint: 3  |  Priority: Must  |  Module Lead: #1  |  Stakeholders: Customer, Waiter, Chef, Manager, Admin

Sprint Goal: Enable customers to place orders and waiters to confirm and track them end to end.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US3.1 | As a Customer, I want to place an order (dine-in or online), so that I can order food without waiting for staff availability. | - Given a menu with available items, when I add items and submit, then an order is created with status 'placed' and correct line items/total. - Given an item that becomes unavailable mid-session, when I try to add it, then I'm blocked with a clear message. | 8 | Must |
| US3.2 | As a Waiter, I want to confirm a placed order, so that it is officially accepted and routed to the kitchen. | - Given a placed order, when a waiter confirms it, then its status changes to 'confirmed' and it becomes visible to the kitchen. - Given a waiter wants to adjust an order before confirming, then line items can be edited prior to confirmation only. | 5 | Must |
| US3.3 | As a Waiter, Chef, or Manager, I want to track order status through its lifecycle, so that everyone knows where each order stands. | - Given an order, when its status changes (placed → confirmed → preparing → ready → served → closed), then all authorized roles see the updated status without a page reload delay of more than a few seconds. | 5 | Must |
| US3.4 | As a Chef or Waiter, I want item-level status within an order, so that partially-ready orders can still be tracked accurately. | - Given a multi-item order, when one item is marked ready before others, then the order view reflects per-item status, not just one order-level status. | 3 | Must |
| US3.5 | As a Waiter, I want to attach an order to a specific table, so that service staff know where to deliver food. | - Given a dine-in order, when a waiter assigns a table, then the order is linked to that table and shows on the table's active-order view. - Given an online (non-dine-in) order, then no table assignment is required. | 3 | Must |

## Module 4: Kitchen Workflow

Sprint: 4  |  Priority: Must  |  Module Lead: #2  |  Stakeholders: Chef, Waiter, Manager, Admin

Sprint Goal: Deliver a Kitchen Display System (KDS) so chefs can receive, prepare, and mark orders ready.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US4.1 | As a Chef, I want to see incoming confirmed orders in a kitchen queue, so that I know what to prepare next. | - Given an order is confirmed by a waiter, when it is saved, then it appears in the Kitchen Display System queue within seconds. - Given multiple confirmed orders, when displayed, then they are ordered oldest-first by default. | 8 | Must |
| US4.2 | As a Chef, I want to mark an item as in-preparation, so that the team knows which dishes are actively being cooked. | - Given a queued item, when a chef marks it in-preparation, then its status updates and is visible to waiter and manager views. | 3 | Must |
| US4.3 | As a Chef, I want to mark items as ready, so that waiters know when to collect and serve them. | - Given an item in-preparation, when a chef marks it ready, then the status updates and the item appears in a 'ready for pickup' list. | 3 | Must |
| US4.4 | As a Waiter, I want to be notified when items are ready, so that food is served promptly and doesn't sit under the lamp. | - Given an item marked ready, when the status changes, then the assigned waiter receives an in-app notification/badge. | 5 | Must |
| US4.5 | As a Chef or Manager, I want to prioritize and time orders in the kitchen queue, so that older or rush orders are handled first and delays are visible. | - Given orders in the queue, when displayed, then each shows elapsed time since confirmation, and orders exceeding a configurable threshold are visually flagged. - Given a manager or chef, when they manually reprioritize an order, then its position in the queue updates accordingly. | 5 | Must |

## Module 5: Billing

Sprint: 5  |  Priority: Must  |  Module Lead: #1  |  Stakeholders: Waiter, Manager, Admin

Sprint Goal: Generate itemized bills from orders, support split bills, and settle payments.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US5.1 | As a Waiter or Customer, I want an itemized bill auto-generated from a served order, so that the customer can review and settle it accurately. | - Given a served order, when billing is triggered, then a bill is generated listing every line item, quantity, and price. - Given an order with modifiers, when billed, then modifier price deltas are correctly reflected in each line. | 8 | Must |
| US5.2 | As a Manager, I want tax, service charge, and tip applied to bills, so that totals comply with restaurant policy. | - Given restaurant-configured tax and service-charge rates, when a bill is generated, then both are calculated and shown as separate line items. - Given an optional tip entered by the customer/waiter, when added, then it is included in the final total. | 5 | Must |
| US5.3 | As a Waiter, I want to split a bill across multiple payers, so that groups can each pay their own share. | - Given a bill, when a waiter splits it evenly or by selected items, then each resulting sub-bill sums correctly to the original total. | 5 | Must |
| US5.4 | As a Waiter or Manager, I want to mark a bill as paid or unpaid, so that the restaurant has an accurate settlement record. | - Given a generated bill, when payment is recorded, then its status changes to 'paid' and it is excluded from outstanding-balance views. | 3 | Must |
| US5.5 | As a Waiter or Customer, I want to issue a receipt or process a refund, so that customers have proof of payment and errors can be corrected. | - Given a paid bill, when a receipt is requested, then a formatted receipt (line items, totals, date) is produced. - Given a valid reason, when a manager processes a refund, then the bill status and reported revenue are updated accordingly. | 3 | Must |

## Module 6: Table Management

Sprint: 6  |  Priority: Should  |  Module Lead: #5  |  Stakeholders: Waiter, Manager, Admin

Sprint Goal: Provide a floor-plan status board so staff can see and manage table state at a glance.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US6.1 | As a Manager or Admin, I want to add and edit tables and floor zones, so that the floor plan matches the physical restaurant layout. | - Given the table admin screen, when a table is created with number, capacity, and zone, then it appears on the floor plan. | 5 | Should |
| US6.2 | As a Waiter or Manager, I want to view the floor plan with live table status, so that I can seat guests and manage the floor efficiently. | - Given the floor plan view, when a table's status changes (free/occupied/reserved), then the visual indicator updates without a manual refresh. | 5 | Should |
| US6.3 | As a Waiter, I want to assign a table to an order, so that the order and the physical table stay linked. | - Given an unassigned dine-in order, when a table is selected, then the order-to-table link is created and reflected on the floor plan. | 3 | Should |
| US6.4 | As a Waiter, I want to mark a table occupied or free, so that the floor status stays accurate as guests arrive and leave. | - Given a table with an active order, when the order is closed, then the table automatically becomes free unless manually held. | 3 | Should |

## Module 7: Reservations

Sprint: 7  |  Priority: Should  |  Module Lead: #4  |  Stakeholders: Customer, Waiter, Manager, Admin

Sprint Goal: Let customers book tables by date/time/party size and let staff manage reservation lifecycle.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US7.1 | As a Customer, I want to book a reservation by date, time-slot, and party size, so that I can guarantee a table before arriving. | - Given available slots, when a customer submits date, time, and party size, then a reservation is created with status 'requested'. - Given a fully-booked slot, when requested, then the system rejects the booking with an alternative-slot suggestion. | 5 | Should |
| US7.2 | As a Manager or Waiter, I want to manage reservation status, so that the reservation book stays accurate. | - Given a requested reservation, when staff confirm it, then its status changes to 'confirmed' and the customer is notified. | 3 | Should |
| US7.3 | As a Waiter or Manager, I want to assign a table to a reservation, so that the right table is held for the right party size. | - Given a confirmed reservation, when a table is assigned, then that table shows 'reserved' on the floor plan at the booked time. | 5 | Should |
| US7.4 | As a Manager, I want to handle no-shows and cancellations, so that tables are freed up for other guests. | - Given a reservation past its grace period with no check-in, when marked no-show, then the held table is released. - Given a customer cancels, when processed, then the reservation status updates and the table is released immediately. | 3 | Should |

## Module 8: Inventory

Sprint: 8  |  Priority: Should  |  Module Lead: #3  |  Stakeholders: Manager, Admin

Sprint Goal: Track ingredient stock, auto-deduct on sales, and alert on low stock.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US8.1 | As a Manager, I want to manage ingredient stock records (CRUD), so that the system has an accurate baseline of what's on hand. | - Given the inventory screen, when an ingredient is added, edited, or removed, then the stock list reflects the change immediately. | 5 | Should |
| US8.2 | As a Manager, I want to map dishes to ingredients (a bill of materials), so that selling a dish can be translated into stock consumption. | - Given a menu item, when a manager defines its ingredient quantities, then that recipe (BOM) is saved and reusable across orders. | 8 | Should |
| US8.3 | As a System (Manager-facing), I want stock to auto-deduct per dish sold, so that inventory stays in sync with actual usage without manual entry. | - Given a dish with a defined BOM, when an order for it is closed, then each mapped ingredient's stock is reduced by the recipe quantity. | 8 | Should |
| US8.4 | As a Manager, I want low-stock alerts, so that I can reorder before running out mid-service. | - Given an ingredient falls below its configured threshold, when checked, then a low-stock alert is shown on the manager dashboard. | 3 | Should |
| US8.5 | As a Manager, I want a supplier reorder form, so that restocking is fast and consistent. | - Given one or more low-stock ingredients, when a manager generates a reorder form, then it lists ingredient, current stock, and suggested reorder quantity. | 3 | Should |

## Module 9: Staff Management

Sprint: 9  |  Priority: Could  |  Module Lead: #5  |  Stakeholders: Manager, Admin

Sprint Goal: Manage staff onboarding, roles/permissions, shift scheduling, and performance tracking.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US9.1 | As a Admin or Manager, I want to onboard and approve new staff, so that only vetted staff can access operational systems. | - Given a new staff application, when an admin approves it, then an account is created with the appropriate role. | 5 | Could |
| US9.2 | As a Admin, I want to assign roles and permissions to staff, so that access matches each person's job function. | - Given an approved staff member, when their role is set (Waiter/Chef/Manager), then their permitted views and actions update accordingly. | 5 | Could |
| US9.3 | As a Manager, I want to set shift schedules, so that staffing matches expected demand. | - Given a staff member, when a manager assigns a shift (date/time), then it appears on that staff member's schedule view. | 5 | Could |
| US9.4 | As a Admin, I want to suspend or remove staff, so that access is revoked promptly when needed. | - Given a staff account, when suspended or removed, then login access is blocked immediately. | 3 | Could |
| US9.5 | As a Manager, I want to track staff performance, so that I can recognize strong performers and address gaps. | - Given staff activity (orders served, shifts completed), when viewed on a performance summary, then basic metrics per staff member are displayed. | 3 | Could |

## Module 10: Analytics + Project Retrospective

Sprint: 10  |  Priority: Could  |  Module Lead: #7  |  Stakeholders: Manager, Admin

Sprint Goal: Deliver the KPI dashboard, complete final integration, and close the project with a final review/retrospective.

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US10.1 | As a Manager, I want revenue and order trend charts (day/week/month), so that I can track business performance over time. | - Given closed orders/bills, when the dashboard loads, then revenue and order-count trends are charted by the selected period. | 5 | Could |
| US10.2 | As a Manager, I want a top-selling-dishes report, so that I know what to promote or restock. | - Given a date range, when viewed, then dishes are ranked by quantity sold and by revenue. | 3 | Could |
| US10.3 | As a Manager, I want table turnover and utilization metrics, so that I can optimize floor usage. | - Given table/order history, when viewed, then average turnover time and occupancy rate per table/zone are shown. | 5 | Could |
| US10.4 | As a Manager, I want peak-hours analysis, so that I can plan staffing around demand. | - Given order timestamps, when charted, then order volume by hour-of-day is displayed to reveal peak periods. | 3 | Could |
| US10.5 | As a Manager, I want an inventory health summary, so that I can see stock risk at a glance. | - Given current stock levels, when viewed, then ingredients nearing or below threshold are highlighted on the dashboard. | 3 | Could |
| US10.6 | As a Manager, I want a reservation no-show rate metric, so that I can assess reservation policy effectiveness. | - Given reservation history, when viewed, then the no-show percentage over a selected period is displayed. | 3 | Could |

## Module 11: Quality, Security & Operations

Sprint: 11  |  Priority: Must  |  Module Lead: #7  |  Stakeholders: Admin, Manager, Waiter, Chef, Customer

Sprint Goal: Close the test gaps module by module, lock every role to the access it needs, and give the team a live API status page.

Status: Delivered

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US11.1 | As an Admin, I want every API endpoint to enforce a written role policy, so that no role can reach features outside its job. | - Given any role-guarded endpoint, when a guest calls it, then it answers 401; when a signed-in role outside the policy calls it, then it answers 403. - Given a developer adds a guarded route, when it is missing from the access matrix, then CI fails. | 8 | Must |
| US11.2 | As a Manager, I want refunds, payment reversals and cancelling paid orders limited to management, so that floor staff cannot move money back out. | - Given a paid bill, when a waiter tries to mark it unpaid, then the request is refused and the bill stays paid. - Given a paid open order, when a waiter cancels it, then it is refused; when a manager cancels it, then it is cancelled and refunded. - Given a customer, when they cancel their own prepaid order before the kitchen takes it, then it is cancelled and refunded. | 5 | Must |
| US11.3 | As a Manager, I want customer records with order history protected from deletion, so that past orders always point at a real customer. | - Given a customer with orders, when a manager deletes them, then the request is refused with an explanation. - Given a waiter, when they view a customer, then no delete action is offered. | 3 | Must |
| US11.4 | As a Manager, I want recipes visible only to the kitchen and management, so that recipe and costing information stays internal. | - Given a waiter, customer or guest, when they load the menu, then no recipe data is included; chefs and managers still see it. | 3 | Must |
| US11.5 | As a Manager, I want the public booking and job-application forms rate limited, so that they cannot be used to flood staff with notifications. | - Given a guest, when they submit more than the allowed bookings or applications in the window, then further submissions answer 429 with a retry time. - Given signed-in staff, when they create bookings, then they are never limited. | 3 | Must |
| US11.6 | As a QA/DevOps engineer, I want a live API status page, so that I can see every endpoint, what it expects and whether it is up. | - Given a browser, when it opens /api/health, then it sees every endpoint grouped by module with roles, inputs, an example response and live status. - Given a script, when it calls /api/health, then it still receives JSON with status, service and time. - Given the live checks run, then only read-only endpoints are called and no data changes. | 5 | Must |
| US11.7 | As a Manager, I want settings and menu edits to reject invalid values, so that a typo cannot silently zero the tax rate. | - Given a settings or category update with a blank, null or non-numeric number, when it is saved, then it is rejected and nothing changes. | 3 | Must |

## Module 12: Staff Accounts & Hierarchy

Sprint: 12  |  Priority: Must  |  Module Lead: #5  |  Stakeholders: Waiter, Chef, Manager, Admin

Sprint Goal: Give every staff member an account page, and let seniors manage the accounts below them, never above.

Status: Delivered

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US12.1 | As a staff member, I want a My account page showing my role and what it lets me do, so that I know my permissions. | - Given any staff role, when they open My account, then they see their name, role, status and the list of what the role can and cannot do. | 3 | Must |
| US12.2 | As a staff member, I want to edit my own name, email and phone, so that my details stay current. | - Given a staff member, when they save a new name or phone, then it is stored. - Given they change their email, when they have not entered their current password, then the change is refused. | 3 | Must |
| US12.3 | As a staff member, I want to change my password, so that only I can use my account. | - Given the wrong current password, a password under 6 characters or an unchanged one, when submitted, then it is refused. - Given a successful change, then this session stays signed in and every other session is signed out. | 5 | Must |
| US12.4 | As a Manager or Admin, I want to edit details and reset passwords for staff below my rank, so that I can help my team without seeing their passwords. | - Given a manager, when they act on a waiter or chef, then they can edit details and issue a one-time temporary password. - Given a reset, then the user is signed out and must set their own password at next sign-in. | 5 | Must |
| US12.5 | As an Admin, I want nobody to manage an account at or above their own rank, so that seniors cannot be locked out by juniors or peers. | - Given the rank admin > manager > chef = waiter, when anyone edits, resets, changes the role of, suspends or removes an account that is not strictly below theirs, then it is refused. - Given an admin, when they act on another admin, then it is refused. | 5 | Must |
| US12.6 | As an Admin, I want new hires and reset accounts flagged until they set their own password, so that temporary passwords do not linger. | - Given an approved hire or a reset account, when they sign in, then a banner asks them to set their own password until they do. | 2 | Must |

## Module 13: Attendance & My Work

Sprint: 13  |  Priority: Should  |  Module Lead: #5  |  Stakeholders: Waiter, Chef, Manager, Admin

Sprint Goal: Let staff check in and out every day, record unpaid breaks, see their own hours, lateness and estimated pay, and see where colleagues at their level are right now.

Status: Planned

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US13.1 | As a staff member, I want to check in, take a break and check out each day, so that my working time is recorded. | - Given a staff member who is off, when they check in, then a session starts; they can start and end a break, then check out. - Given an invalid step (for example checking in twice), when attempted, then it is refused with a message. | 5 | Should |
| US13.2 | As a Manager, I want breaks to be unpaid and a standard 1-hour break applied when none is recorded on a long day, so that paid time is fair and consistent. | - Given recorded breaks, when paid time is calculated, then break time is excluded. - Given more than 6 worked hours and no recorded break, then a 1-hour unpaid break is deducted and marked as automatic (both values are settings). | 3 | Should |
| US13.3 | As a Manager, I want late arrivals flagged automatically, so that punctuality is measured the same way for everyone. | - Given a scheduled shift and a grace period from settings (default 5 minutes), when a staff member checks in after start + grace, then the session is marked late with the minutes late. | 3 | Should |
| US13.4 | As a staff member, I want a My work page with my hours, punctuality and attendance as charts and progress rings, broken down by day, week, month and hour of day, so that I can see how I am doing. | - Given my shifts and sessions, when I open My work, then I see rings for hours vs scheduled, on-time rate and attendance rate. - Given the breakdown switch, when I choose day, week, month or hour of day, then the chart shows paid vs scheduled time for that grouping, with a table alternative. - Given my sessions, then each shows check-in, check-out, breaks, late minutes and paid hours. | 8 | Should |
| US13.5 | As a staff member, I want to see which colleagues at my level are working, on break or off right now, so that I know who is around. | - Given a waiter, then they see every waiter's current state, since when, and today's shift; a chef sees chefs; a manager sees managers, waiters and chefs; the admin sees everyone. | 3 | Should |

## Module 14: Payroll & Workforce Hub

Sprint: 14  |  Priority: Should  |  Module Lead: #1  |  Stakeholders: Waiter, Chef, Manager, Admin

Sprint Goal: Turn paid hours, tips and bonuses into an estimated monthly pay for each person, and give the admin one hub that shows everything about everyone.

Status: Planned

| ID | User Story | Acceptance Criteria | Pts | Pri. |
| --- | --- | --- | --- | --- |
| US14.1 | As a staff member, I want my estimated pay for the month, so that I know what I will earn. | - Given a month, then pay = paid hours × hourly wage + tips + bonuses − late deductions, each line itemised, marked "estimated" until the month ends. - Given a waiter, then tips from bills they served are included. | 5 | Should |
| US14.2 | As an Admin, I want a deduction for each late arrival, so that the late policy is applied consistently. | - Given the late-arrival penalty in settings (default 5.00), when a month is calculated, then each late session deducts it and is listed. | 3 | Should |
| US14.3 | As an Admin, I want to set each staff member's hourly wage and give bonuses (for example for Eid or a birthday), so that pay reflects my decisions. | - Given the admin, when they change a wage or add or remove a bonus with amount, reason and date, then it appears on that person's pay; nobody else can. | 3 | Should |
| US14.4 | As an Admin, I want a Workforce hub with live presence, team charts, progress rings and a staff table with pay, so that I can see everything about everyone in one place. | - Given the admin and a month, then they see KPIs, who is working now, team hours by day and week, lateness trends, and every person with hours, late count, wage, tips, bonuses and net pay, with totals. - Given a person in the table, when opened, then the admin sees the same breakdowns as that person's My work page. | 8 | Should |
| US14.5 | As a Manager, I want the Workforce hub for waiters and chefs without any pay figures, so that I can run the rota while pay stays private. | - Given a manager, then the hub shows waiters' and chefs' attendance, hours and lateness, and no wage, tips, bonus or pay figure anywhere. - Given a waiter or chef, when they request someone else's analytics or pay, then it is refused. | 3 | Should |

# 3. Backlog Management Notes

- Refinement cadence: the top 1–2 upcoming sprints' worth of stories are refined (clarified, re-estimated, re-ordered) during each week's Backlog Refinement session, ahead of the next Sprint Planning.

- Re-prioritization: if a stakeholder review (Sprint Review) surfaces new requirements or a scope change, the Product Owner re-orders the remaining backlog before the next sprint begins — this is how the team demonstrates ‘responding to change’.

- Definition of Ready: a story is eligible for Sprint Planning only once it has a clear ‘As a / I want / so that’ statement, testable acceptance criteria, and an agreed story-point estimate.

- This document is the source of truth for backlog content; the per-sprint Sprint Backlog document pulls its committed stories directly from here.