Restaurant Operations & Ordering Platform

Project Timeline & Gantt Schedule

10 weekly sprints, milestones, dependencies, and per-member ownership

Sprint length: 1 week  ·  Total duration: 10 weeks

# 1. Sprint Gantt Chart

Each shaded cell marks the week in which that module is the active sprint focus. Sprint order follows the dependency chain: platform/auth and customer data first, then the core order-to-cash path (Menu → Order → Kitchen → Billing), then floor/booking operations, then back-of-house administration, and finally analytics + closeout.

| Module (Sprint) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer Management (S1) |  |  |  |  |  |  |  |  |  |  |
| Menu Management (S2) |  |  |  |  |  |  |  |  |  |  |
| Order Management (S3) |  |  |  |  |  |  |  |  |  |  |
| Kitchen Workflow (S4) |  |  |  |  |  |  |  |  |  |  |
| Billing (S5) |  |  |  |  |  |  |  |  |  |  |
| Table Management (S6) |  |  |  |  |  |  |  |  |  |  |
| Reservations (S7) |  |  |  |  |  |  |  |  |  |  |
| Inventory (S8) |  |  |  |  |  |  |  |  |  |  |
| Staff Management (S9) |  |  |  |  |  |  |  |  |  |  |
| Analytics (S10) |  |  |  |  |  |  |  |  |  |  |

# 2. Module Ownership by Sprint

| Sprint | Week | Module | Owner | Support |
| --- | --- | --- | --- | --- |
| 1 | Week 1 | Customer Management | #4 | #6 (UI), #7 (QA/CI bootstrap), #1 (PO/WPDS), #2 (SM/facilitation) |
| 2 | Week 2 | Menu Management | #3 | #6 (UI), #7 (QA), #1 (PO/WPDS), #2 (SM/facilitation) |
| 3 | Week 3 | Order Management | #1 | #6 (UI), #7 (QA), #2 (SM/facilitation) |
| 4 | Week 4 | Kitchen Workflow | #2 | #6 (UI), #7 (QA), #1 (PO/WPDS) |
| 5 | Week 5 | Billing | #1 | #6 (UI), #7 (QA), #2 (SM/facilitation) |
| 6 | Week 6 | Table Management | #5 | #6 (UI), #7 (QA), #1 (PO/WPDS) |
| 7 | Week 7 | Reservations | #4 | #6 (UI), #7 (QA), #2 (SM/facilitation) |
| 8 | Week 8 | Inventory | #3 | #6 (UI), #7 (QA), #1 (PO/WPDS) |
| 9 | Week 9 | Staff Management | #5 | #6 (UI), #7 (QA), #2 (SM/facilitation) |
| 10 | Week 10 | Analytics | #7 | #6 (UI), #1 (PO/WPDS, final report), #2 (SM, final retro) |

Cross-cutting roles every sprint: #6 (UI/UX) builds the frontend for that week's module; #7 (QA/DevOps) tests and deploys it; #1 (PO) writes the WPDS entry; #2 (SM) facilitates all ceremonies.

# 3. Key Dependencies

- Auth/RBAC (Sprint 1) is a hard prerequisite for every later module — all role-based views depend on it.

- Menu Management (Sprint 2) must exist before Order Management (Sprint 3) can let customers add real items.

- Order Management (Sprint 3) must exist before Kitchen Workflow (Sprint 4) has anything to display in the queue.

- Kitchen Workflow (Sprint 4) and Order Management (Sprint 3) together are prerequisites for Billing (Sprint 5), which bills served orders.

- Table Management (Sprint 6) formalizes the table concept first introduced informally in Order Management (table attach, Sprint 3); Reservations (Sprint 7) then builds on Table Management.

- Inventory (Sprint 8) depends on Menu Management (for dish/ingredient mapping) and Order/Billing (to trigger auto-deduction on sale).

- Staff Management (Sprint 9) depends on the Auth/RBAC foundation (Sprint 1) to extend role administration.

- Analytics (Sprint 10) depends on data produced by every prior module (orders, billing, inventory, reservations) and is therefore scheduled last.

# 4. Milestones

| Week(s) | Milestone | Deliverable / Evidence |
| --- | --- | --- |
| Week 1 | Foundation live | Auth/RBAC + Customer Management deployed; Sprint 1 Review/Retro/WPDS |
| Weeks 2–5 | Core order journey complete | Menu → Order → Kitchen → Billing chain fully working end-to-end |
| Weeks 6–7 | Floor & booking operations live | Table Management + Reservations integrated with live orders |
| Weeks 8–9 | Back-of-house complete | Inventory auto-deduction verified against Billing; Staff Management live |
| Week 10 | Final delivery | Analytics dashboard, full regression test, final demo, complete documentation set |