Restaurant Operations & Ordering Platform

Story Points, Velocity & Burndown Framework

Estimation scale, planned points per sprint, and templates for tracking actual velocity and burndown

# 1. Story-Point Estimation Approach

The team estimates every user story using a Fibonacci-like scale: 1, 2, 3, 5, 8, 13. Points represent relative effort/complexity/uncertainty, not hours, and are agreed by the whole team via Planning Poker during Sprint Planning and Backlog Refinement.

| Points | Meaning |
| --- | --- |
| 1 | Trivial change; well understood, no unknowns (e.g., a single field/label change). |
| 2 | Small, isolated change; low risk. |
| 3 | Small feature with minor integration; some design decisions needed. |
| 5 | Moderate feature; touches multiple layers (UI + API + data) or has real business logic. |
| 8 | Substantial feature; real-time behavior, multiple roles, or non-trivial integration (e.g., KDS queue, billing calculation, inventory auto-deduction). |
| 13 | Large/uncertain; should usually be split into smaller stories before being committed to a sprint. |

# 2. Planned Points by Sprint

This is the baseline plan derived from the Product Backlog. It gives the team a target velocity to compare actuals against.

| Sprint | Module | Planned Points | Cumulative Planned |
| --- | --- | --- | --- |
| 1 | Customer Management | 24 | 24 |
| 2 | Menu Management | 19 | 43 |
| 3 | Order Management | 24 | 67 |
| 4 | Kitchen Workflow | 24 | 91 |
| 5 | Billing | 24 | 115 |
| 6 | Table Management | 16 | 131 |
| 7 | Reservations | 16 | 147 |
| 8 | Inventory | 27 | 174 |
| 9 | Staff Management | 21 | 195 |
| 10 | Analytics | 22 | 217 |

Total planned points across the project: 217  |  Average planned velocity: 21.7 points/sprint.

# 3. Velocity Tracking Template

Fill in Completed Pts and Carried Over at the end of each Sprint Review. Velocity for a sprint = Completed Pts (stories that fully met the Definition of Done). Carried-over points return to the Product Backlog and are re-planned, not silently dropped.

| Sprint | Planned Pts | Completed Pts | Carried Over | Velocity (this sprint) |
| --- | --- | --- | --- | --- |
| 1 | 24 | ____ | ____ | ____ |
| 2 | 19 | ____ | ____ | ____ |
| 3 | 24 | ____ | ____ | ____ |
| 4 | 24 | ____ | ____ | ____ |
| 5 | 24 | ____ | ____ | ____ |
| 6 | 16 | ____ | ____ | ____ |
| 7 | 16 | ____ | ____ | ____ |
| 8 | 27 | ____ | ____ | ____ |
| 9 | 21 | ____ | ____ | ____ |
| 10 | 22 | ____ | ____ | ____ |

Rolling velocity: after Sprint 3, calculate a 3-sprint rolling average of Velocity to use for future Sprint Planning capacity discussions instead of the original flat estimate.

# 4. Burndown Tracking (per sprint)

For each sprint, track remaining story points day-by-day from Sprint Planning to Sprint Review. Use a simple table (below) or a chart with Day on the x-axis and Remaining Points on the y-axis; plot both the Ideal line (linear decrease from committed points to zero) and the Actual line.

| Day | Ideal Remaining Pts | Actual Remaining Pts | Notes / Blockers |
| --- | --- | --- | --- |
| Day 1 (Planning) | ____ | ____ |  |
| Day 2 | ____ | ____ |  |
| Day 3 | ____ | ____ |  |
| Day 4 | ____ | ____ |  |
| Day 5 | ____ | ____ |  |
| Day 6 | ____ | ____ |  |
| Day 7 (Review) | ____ | ____ |  |

# 5. Project-Level Burn-Up View

In addition to per-sprint burndown, maintain one running project-level table: cumulative points completed vs. cumulative points planned (the same 'Cumulative Planned' column from Section 2, compared against a running 'Cumulative Completed' figure). Plotting both lines across all 10 sprints visually shows whether the team is on pace to complete the full backlog, ahead, or behind — useful evidence for demonstrating iterative/incremental delivery.

| Sprint | Cumulative Planned | Cumulative Completed (fill in) |
| --- | --- | --- |
| 1 | 24 | ____ |
| 2 | 43 | ____ |
| 3 | 67 | ____ |
| 4 | 91 | ____ |
| 5 | 115 | ____ |
| 6 | 131 | ____ |
| 7 | 147 | ____ |
| 8 | 174 | ____ |
| 9 | 195 | ____ |
| 10 | 217 | ____ |

# 6. What This Demonstrates for Evaluation

- Story-point estimation — shown in Section 1 and applied per story in the Product Backlog.

- Velocity tracking — shown in Section 3, updated weekly.

- Burndown/burn-up — shown in Sections 4–5, updated per sprint and cumulatively.

- Responding to change — carried-over or re-scoped points are visible and explained, not hidden.